## Milestones
List milestones and deliveries of project
Milestone ID | Date | Description | Completed
1 | 07-10-2011 | Kick-off project | OK
2 | 31-11-2011 | First integration and start testing | Failed
3 | 16-12-2011 | Second integration and first demo to customer | Failed
4 | 31-03-2012 | First integration + Testing + Fix bug
5 | 15-04-2012 | Second integration and first demo to customer
6 | 05-05-2012 | Third integration + Testing + Fig bug
7 | 31-05-2012 | Second Demo to customer
8 | 31-06-2012 | Acceptance test by customer

## PlannedTask
ProjectName: Sales management
Development team: Bằng, Hoàng, (Linh), Phúc, Tuyết.
TaskID | Decription | Task predecessor | Responsible | Start date | Finish date | Estimate time | Spent time | % done
1 | Design framework - project structure |  |  | 01-08-2011 | 31-03-2012 | 200 | 100 | 50%
2 | Specification (Write, update + ask, answer questions from customer) |  |  | 15-09-2011 | 15-04-2012 | 100 | 90 | 90%
3 | Database sql + ER diagram |  |  | 19-01-2012 | 20-03-2012 | 80 | 40 | 50%
4 | Simple screens for Product, Category management. |  |  | 19-01-2012 | 31-03-2012
5 | Simple screens for Store management |  |  | 19-01-2012
6 | Simple screens for customer management. |  |  | 19-01-2012
7 | Simple screens for invoice management. |  |  | 19-01-2012
8 | Simple screens for Access privilege management |  |  | 19-01-2012
9 | Screens for "Red alert"
10 | Report management
11 | MySQL tunning technique
12 | Define Installation process
13 | Customer guildlines.
14 | Test plan + Test cases + Testing
15 | Fix bugs |  |  | 15-03-2012
180

## NotPlannedTask
TaskID | Decription | Task predecessor | Responsible | Start date | Finish date | Estimate time | Spent time | % done
Integrate Mantis + SVN
0