## WBS
ProjectName: Sales management
Development team: Bằng, Hoàng, (Linh), Phúc, Tuyết.
TaskID | Decription | Task predecessor | Responsible | Start date | Finish date | Estimate time | Spent time | % done
1 | Specification (Write, update + ask, answer questions from customer)
2 | Database sql + ER diagram
3 | Simple screens for Product, Provider management.
4 | Simple screens for Store management
5 | Simple screens for customer management.
6 | Simple screens for invoice management.
7 | Simple screens for Access privilege management
8 | Screens for "Red alert"
9 | Report management
10 | MySQL tunning technique
11 | Define Installation process
12 | Customer guildlines.
13 | Test plan + Test cases + Testing
14 | Fix bugs
15 | Integrate Mantis + SVN
0

## Milestones
List milestones and deliveries of project
Milestone ID | Date | Description | Completed
1 | 07-10-2011 | Kick-off project
2 | 11-11-2011 | First integration and start testing
3 | 16-12-2011 | Second integration and first demo to customer